## Sprint 1
Functional Testing Case Study - 1
Task/Scenario Given: |  | The following website is given for Manual Testing to follow Agile practices and design and execute Test Cases and create Defect Report https://freecrm.co.in/index.html
Sprint Day | Sprint Activity | Overview and scope of functionality
Sprint Day 1 | Project Management Activity: Product Owner 1. Create user stories based open functionality I. Understanding requirements II. Assign priority III. Assign user stories to team members 2. Identify the De+B3pendacy between the requirement 3. Final ordering of product backlog item( set of all user stories) Create Task / Deliverables: 1. List of User Stories & Functions to test 2. All tasks with JIRA should be ready in SCRUM template | Project Overview: Free CRM delivers cloud-based and as well as a full range of software and choice in how you want it - licensed, on-demand, private label, and custom services. In scope Functionality: A. Login Module 1. User should be able to Login to FreeCRM by entering valid credentials on Login Panel. B.Add a new company by entering required details i)Click on contacts and create New contacts by entering details. ii)Click on Deal tab and Create a new deal. iii)Click on Tasks tab and create new tasks iv)Veirfy on calender weather the created tasks are reflecting on calender page. Out of Scope Functionality: Load Testing and Security Testing on Leave Management System. Expected Implementations : 1. Usage of all Testing Types 2. Usage of Test Design Techniques like EP, BVA etc. 3. Usage of Valid invalid input data 4. Test case design in Integration and system level testing
Sprint Day 2 | JIRA Task and Test Design : Dev Team 1. Assign story point or time required to accomplish the story/Task 2. Categorize user stories in to Epic, User Stories, Tasks & SubTasks 3. Assign the stories to components 4. Add group members in th Project on JIRA. 5. Create MAnual Test Scenarios Create Task / Deliverables: 1. Test scenarios 2. Test Case design
Sprint Day 3 | Scrum Team activities : Dev Team 1. Create scrum based sprints 2. Create Sprint backlog (select the stories for the particular Sprint) 3. Create Sprint board (Todo , in process, Done) Create Task / Deliverables: 1. Test Case design 2. Test Case execution
Sprint Day 4 | Scrum Team Activity : Scrum Team (PO, SM, DT) 1. Plan for release 2. Generate Agile report relevant to scrum project (e.g. Burn down chart, Sprint report etc.) Create Task / Deliverables: 1. Defect reporting 2. Traceability Matrix 3. Test summary report Keep all the Deliverables on Git
Sprint Day 5 | Sprint Evaluation

## User Story
Issue type | Summary | Description
|  | Objective | Acceptance
Story | UI of Deals | Any registered user can access the home page of Deals and create a new deal. | Acceptance 1:- When I click on Deals there should be options like Pipeline, View, Show Filters, Board, Manage Targets, Export and New on the Top.
Acceptance 2:- There should be headings like Title, Company, CloseDate, Amount, Status, Stage and Options.
The data of the created deals by the user should be displayed below these headings.
Acceptance 3:- If there are No Deals created by the user it should display "No records found".
Acceptance 4:- When I click on New I should be able to create a New Deal.
Story | Create New Deals | When as a User, I enter all the details a New Deal should be created and this data should be dispayed on UI of Deals under respective headings. | Acceptance 1:-
In Create New Contact page there should be fields like Title, Access, Assigned To, Company, Products, Contacts, Close Date, Tags, Description,
Probability, Amount, Commission, Stage, Closed, Status, Next Steps, Type, Source, Identifier.
There should be Save and Cancel Button on the Top.
The user can fill/select data in respective fields.
Acceptance 2:-
When I click on Title I should be able to enter the details.
It can accept alphanumeric characters and is a Mandatory field.
When the field is empty "The field Title is required" alert message should be displayed on the top.
Acceptance 3:-
In Access there should be an option from which I can select the type of account like Public or Private.
I should be able to select the names of registered users from the dropdown.
When no users are selected it should display "Select users allowed access".
Acceptance 4:-
When I click on Assigned To there should be a drop down from which I should be able to select the names of the registered users.
Acceptance 5:-
When I click on Company I should be able to insert the Company name and that name should be saved and
displayed later in the drop down for further reference and the user can select from the options then.
It can accept alphanumeric characters.
When No company is entered it should display "No results found." in the drop down.
Acceptance 6:-
When I click on Products I should be able to insert the Product name and that name should be saved and
displayed later in the drop down for further reference and the user can select from the options then.
It can accept alphanumeric characters.
When No Product is entered it should display "No results found." in the drop down.
Acceptance 7:-
When I click on Contacts I should be able to insert the Contact name and that name should be saved and
displayed later in the drop down for further reference and the user can select from the options then.
It can accept alphanumeric characters.
When No Contact is entered it should display "No results found." in the drop down.
Acceptance 8:-
When I click on CloseDate I should be able to select the date, month and year along with time.
Date should be displayed in DD/MM/YYYY and Time in 24 hours format.
Acceptance 9:-
When I click on Tags I should be able to insert the Tag name and that name should be saved and
displayed later in the drop down for further reference and the user can select from the options then.
It can accept alphanumeric characters.
When No Tag is entered it should display "No results found." in the drop down.
Acceptance 10:-
When I click on Description I should be able to enter the description about my deal.
No character limit.
It can accept alphanumeric characters.
Acceptance 11:-
When I click on Probability I should be able to enter numbers.
This field can accept on numbers only.
Acceptance 12:-
There should be a box that displayes USD showing that the amount is in USD only.
When I click on Amount, it should only accept numbers.
Acceptance 13:-
There should be a box that displayes USD showing that the amount is in USD only.
When I click on Commission, it should only accept numbers.
Acceptance 14:-
When I click on Stage I should be able to select options from drop down.
The available options are Prospect,Qualify,Research,Quote,Negotiate,Won,Lost
Acceptance 15:-
There should be a slider button option where I should be able to slide and close it.
Acceptance 16:-
When I click on Status I should be able to select opiton from drop down.
The available options are New,Active,Inactive,On Hold,Terminated,Hot.
Acceptance 17:-
When I click on Next Steps I should be able to enter the next steps.
No character limit.
Acceptance 18:-
When I click on Type I should be able to select type from drop down options.
The options are New, Old, Opportunity, Priority
Acceptance 19:-
When I click on Source I should be able to select options from the source.
The options will be Partner,Word Of Mouth,Referral,Existing Customer, Online
Acceptance 20:-
When I click on Identifier it should display the email-id's of registered users and I should be able to select required email-id from them.
Acceptance 21:-
When I click on Save all the details should be saved.
Acceptance 22:-
When I click on Cancel I should be redirected to the main page of Deals.
Acceptance 23:-
When title field is empty and save button is pressed same page should be displayed of Create New Deals

## Test Scenario
Story name | TestScenarioID | Requirement ID | Test Scenario Description | Type of Testing | Possible No. of TestCases | Test Case Details
UI of Deals | TS_01 | COG-38 | Verifying the UI of Deals page | UI | 1 | Verify the UI of Deals Page
| TS_02 |  | Verifying Options / Buttons on Deals page | Functional | 3 | Verify presence of Deals Option
| TS_03 |  |  |  |  | Verify working of Deals Option
| TS_04 |  |  |  |  | Verify working of New Button
Create New Deals | TS_05 | C0G_39 | Verifying Create New Deals Page | UI | 1 | Verify the Create New Deals Page
| TS_06 |  | Verifying Fields/Buttons present in Create New Deals page | Functional | 2 | Verify Title Field
| TS_07 |  |  |  |  | Verify Title Field when no data is entered
| TS_08 |  |  |  | 2 | Verify Access Field
| TS_09 |  |  |  |  | Verify Public/Private Button
| TS_10 |  |  |  | 1 | Verify Assigned To Field
| TS_11 |  |  |  | 1 | Verify Company,Products,Contacts,Tags Field
| TS_12 |  |  |  | 1 | Verify if saved data is present for further reference for Compant,Products,Contacts,Tags field
| TS_13 |  |  |  | 2 | Verify the closed date field
| TS_14 |  |  |  |  | Verify the format of closed date field
| TS_15 |  |  |  | 2 | Verify Description and Next Field
| TS_16 |  |  |  | 1 | Verify Probability Field
| TS_17 |  |  |  | 2 | Verify Amount,Commission Field
| TS_18 |  |  |  | 1 | Verify USD box in amount and commission field
| TS_19 |  |  |  | 4 | Verify Stage,Status,Type ,Source field and the dropdown
| TS_20 |  |  |  | 1 | Verfy close slider option
| TS_21 |  |  |  | 2 | Verify Identfier field
| TS_22 |  |  |  |  | Verify registered users email id can be selected in identifier field
| TS_23 |  |  |  | 1 | Verify Save Button
| TS_24 |  |  |  | 1 | Verify Cancel Button
| TS_25 |  |  |  | 1 | Verify when title field is blank and save option is clicked

## Test Case
Test Case ID | Story/Folder | Objective | Test Name | Precondition | Test Case Steps | Test Data | Expected Result | Actual Result | Status | Priority
COG_001 | /UI for Deals | Check the Deals option on Home page | To verify the Deals option on home page | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. | Deals | It should display the Deals option on left sidebar | Deals | Pass | Highest
COG_002 |  | Check the working of Deals Option | Verify the click of Contact button | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals | Deals | When you click on Deals there should be options like Pipeline,View,Show Filters,Board,Manage Targets,Export and New on the Top. There should be headings like Title,Company,CloseDate,Amount,Status,Stage and Options. | Deals | Pass | High
COG_003 |  | Check the working of New Option | Verify the click of New button | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New | New | When you click on New, Create New Contact page should Open. | New | Pass | High
COG_04 | Create New Deals | Check the User Interface of New Deals | Verify if all the fields are present | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New | Title, Access, Assigned To, Company, Products, Contacts, Close Date, Tags, Description, Probability, Amount, Commission, Stage, Closed, Status, Next Steps, Type, Source, Identifier. Save,Cancel Button. | When you click on New, Create New Contact page should open and there should be fields like Title, Access, Assigned To, Company, Products, Contacts, Close Date, Tags, Description, Probability, Amount, Commission, Stage, Closed, Status, Next Steps, Type, Source, Identifier. There should be Save and Cancel Button on the Top. | Title, Access, Assigned To, Company, Products, Contacts, Close Date, Tags, Description, Probability, Amount, Commission, Stage, Closed, Status, Next Steps, Type, Source, Identifier. Save,Cancel Button. | Pass | High
COG_05 |  | Check if the user is able to enter the data | Verify the Title Field | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New | Title:Test Cases Cogmento | When you click on Title the user should be able to add alphanumeric characters. It is a mandatory field. | Title:Test Cases Cogmento | Pass | Medium
COG_06 |  | Check if the alert message "This field Title is required" is displayed in red letters on the top. | Verify the alert message on the top of Title field. | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click on Title | This field Title is required | "This field Title is required" should be displayed on top of Title field in red letters. | This field Title is required | Pass | Medium
COG_07 |  | Check if the user is able to select the users from registered user names. | Verify the Access Field | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click on Access | Access:Pranita Dorle | When you click on Access the user should be able to select the User Name from registered users and give them access | Access:Pranita Dorle | Pass | Medium
COG_08 |  | Check if the user is able to change the acces from Private to Public and Public to Private | Verify the Private and Public Button | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click on Access | Private<-->Public | Public or Private access can be given. | Private<-->Public | Pass | Medium
COG_09 |  | Check if the user is able to select the users from registered user names. | Verify the Assigned To Field | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click on Assigned To Field | Assigned To:-Pranita Dorle | When you click on Assigned To the user should be able to select the User Name from registered users and give them access | Assigned To:-Pranita Dorle | Pass | Medium
COG_10 |  | Check if the user is able to enter the alphanumeric Company,Products,Contacts,Tags name. | Verify the Company,Products,Contacts,Tags Field | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click on Company/Products/Contacts/Tags Field | Company:- Products: Contacts:- Tags:- | When you click on Company/Products/Contacts/Tags the user should be able to enter the desired company/products/contacts/tags name. | Company:- Products: Contacts:- Tags:- | Fail | Medium
COG_11 |  | Check if the user is able to select Company,Products,Contacts,Tags name from previously entered data. | Verify whether the Company/Products/Tags Name is saved for further reference and is available to be selected. | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click on Company/Products/Tags Field 6.Click on Search | Company:-capg13 Products: Contacts:-9876543211 Tags:- | When you click on Company/Products/Contacts/Tags the user should be able to see the previously entered Company/products/contacts/tags names and the desired option can be selected. | Company:-capg13 Products: Contacts:-9876543211 Tags:- | Pass | Medium
COG_12 |  | Check if the user is able to select the date and time from the drop down option. | Verify the Close Date field | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click CloseDate | CALENDAR & TIME | When you click on Date the usre should be able to select the date and time from the drop down calendar. | CALENDAR & TIME | Pass | Medium
COG_13 |  | Check if the selected date and time is displayed in DD/MM/YYYY for date and 24 hours for time. | Verify if the Date and Time Format is in DD/MM/YYYY and 24 hours format | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click CloseDate 6.Select desired date and time | 2020-12-23 23:00 | When the user selects desired date and time it should be displayed in DD/MM/YYYY format for date and 24 hours format for time. | 2020-12-23 23:00 | Pass | Medium
COG_14 |  | Check if the user is able to enter alphanumeric characters in Description and Next Step fields and there is no character limit. | Verify the Description and Next Steps field | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click Description/Next Steps | Description:-qwertyuiopasdfghjklzxcvbnm Next Steps:-qwertyuiopasdfghjklzxcvbnm | When the user clicks on Description/Next Steps the user should be able to add the data with alphanumeric characters as well | Description:-qwertyuiopasdfghjklzxcvbnm Next Steps:-qwertyuiopasdfghjklzxcvbnm | Pass | Medium
COG_15 |  | Check if the user is able to enter number only. | Verfiy the Probability Field | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click Probability | Probability:-1234 | When the user clicks on Probability the user should be able to enter numbers only. | Probability:-1234 | Pass | Medium
COG_16 |  | Check if the user is able to enter numbers only. | Verify Amount,Commission Field | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click Amount/Commission | 10,1 | When the user clicks on Amount/Commission the user should be able to enter numbers. | 10,1 | Pass | Medium
COG_17 |  | Check if a box with USD is written below Amount/Commission | Verify the presence of USD box below Amount/Commission | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click Amount/Commission | USD | There is a box with USD written in it below Amount & Commission. | USD | Pass | Medium
COG_18 |  | Check if the stage option has a drop down which includes Prospect,Qualify,Research,Quote,Negotiate,Won,Lost and can select any 1 from them | Verify the Stage Option | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click on Stage | Prospect,Qualify,Research,Quote,Negotiate,Won,Lost | When the user clicks on stage the user should be able to select any one of the options present in drop down. | Prospect,Qualify,Research,Quote,Negotiate,Won,Lost | Pass | Medium
COG_19 |  | Check if the status option has a drop down which includes New,Active,Inactive,On Hold,Terminated,Hot. | Verify the Status Option | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click on Status | New,Active,Inactive,On Hold,Terminated,Hot. | When the user clicks on status the user should be able to select any one of the options present in drop down. | New,Active,Inactive,On Hold,Terminated,Hot. | Pass | Medium
COG_20 |  | Check if the Type Option has a drop down that includes New, Old, Opportunity, Priority | Verify the Type Option | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click on Type | New, Old, Opportunity, Priority | When the user clicks on type the user should be able to select any one of the options present in drop down. | New, Old, Opportunity, Priority | Pass | Medium
COG_21 |  | Check if the Source Option has a drop down that includes Partner,Word Of Mouth,Referral,Existing Customer, Online | Verify the Source Option | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click on Source | Partner,Word Of Mouth,Referral,Existing Customer, Online | When the user clicks on source the user should be able to select any one of the options present in drop down. | Partner,Word Of Mouth,Referral,Existing Customer, Online | Pass | Medium
COG_22 |  | Check if the Slider for the Closed options works properly. | Verify the Closed Slider Option | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click on Closed | Closed | When the user clicks on Closed he should be able to move the slider to close it. | Closed | Pass | Medium
COG_23 |  | Check if the registered email id's are available to be selected | Verify the Identifier Option | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click on Identifier | pranita1502@gmail.com | When the user clicks on Identifier he should be able to select the desired email id's from the drop down section. | pranita1502@gmail.com | Pass | Medium
COG_24 |  | Check if the email ids of the registered users are available for available in the drop down. | Verify is Registered Email Id's are available in Identifier | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click on Identifier | pranita1502@gmail.com | When the user clicks on Identifier there should be email id's of the registered users in the drop down section. | pranita1502@gmail.com | Pass | Medium
COG_25 |  | Check if all the data is saved | Verify the Save Button | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click on Save | Saved | When the user clicks on save all the entered data should be saved and must be displayed under respective fields on Deals page. | Saved | Pass | High
COG_26 |  | Check if the user is directed to the Deals page and the data is discarded | Verify the Cancel Button | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Click on Cancel | UI of Deals | When the user clicks on Cancel all the entered data should be discarded and the user is directed to the Deals page. | UI of Deals | Pass | High
COG_27 |  | Check if same page is displayed when no title is entered and Save button is pressed | Verify when no data is entered in Title field and Save button is pressed | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid active account and should be logged in | 1. Go to URL https://ui.freecrm.com/ 2.Login with valid username and password. 3.Click on Deals 4.Click on New 5.Title field is empty 5.Click on Save | Create New Deals page | When the title field is empty and the user clicks on Save then same page of New Deals should be displayed | Create New Deals page | Pass | High

## Defect Report
Defect ID | Summary | ReportedBy | Date | Assigned To | Severity | Priority | Status | Module | Build Version | Reproducable | ReproSteps
COG-57 | When I click on Products in New Create Deals page the data entered in not saved for further reference | dorlep1502@gmail.com | 2020-12-02 | abc@gmail.com | High | High | To do | Create New Deals | Sprint 1 | Yes | 1.Login into the account 1.Click on Deals 2.Click on New 3.Click on Products

## Test Summary Report
Test Summary Report for Sprint1 (27 - Nov to 02-Dec )
S.No. | Activities | Count | Passed | Failed | Duplicate | Remarks
1 | Created User Stories | 10
2 | Created TestCases | 130
3 | No. of tests Executed in Sprint ,iteration 1 | 130 | 123 | 7
4 | Defects Reported | 6
5 | No. of Sprints Executed | 1
Any Challenges
Any Best Practises

## Burn Down Chart
BURNDOWN CHART

## Sprint Report
SPRINT REPORT